## List task
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Equipment Info Entry & Project Initialization | - Build basic data entry forms - Implement role-based login (EPM, Toolroom, CPM, etc.) - Structure for customer, device, legal entity information | OPEN | 阮俊英 | 2025-08-15 | 2025-08-16 | 1
| Development & Cost Evaluation | - Input & track DFM submission/approval dates - Input cost data & approval status - Manage development progress tracking | OPEN | 阮俊英 | 2025-08-18 | 2025-08-19 | 1
| Customer PO & Payment Management | '- Record customer PO, PO date, payment terms - Track payment status, invoice, NRE - Payment confirmation interface | OPEN | 阮俊英 | 2025-08-20 | 2025-08-21 | 1
| Delivery & Customs Clearance | - Create PR/PO entry forms - Auto-calculate processing duration - Alert if delayed processing | OPEN | 阮俊英 | 2025-08-22 | 2025-08-23 | 1
| Internal PR / PO Handling | - Input committed vs. actual ETD - Record document sent date and customs clearance date - Alert on ETD delay (>3, >5 days) | OPEN | 阮俊英 | 2025-08-25 | 2025-08-26 | 1
| Acceptance & Asset Tracking | - Record acceptance document, serial number, storage location - Role-based access (Toolroom / ME) - Auto-reminder if ETA > 30 days | OPEN | 阮俊英 | 2025-08-27 | 2025-08-28 | 1
| Remarks & Access Control | - Restrict Remarks field visibility by role - Only Toolroom & Boss can view internal notes - Field-level permission control | OPEN | 阮俊英 | 2025-08-30 | 2025-08-30 | 0
| Automated Email Alerts | - Auto-email if delayed >3 or >5 days - Notify 2 days before ETD - Remind users for pending acceptance after ETA | OPEN | 阮俊英 | 2025-09-01 | 2025-09-02 | 1
| Final Integration Testing & Demo | - Bug fixing & refinements - Prepare internal demo & user guide documentatio | OPEN | 阮俊英 | 2025-09-03 | 2025-09-04 | 1